## Risks
Risk Assessment Template
Organisation:
Initiative, Project, and/or Engagement:
Author:
Date:
| Risk Statement |  | (Scale) | (Scale)
# | Condition | Consequence | Probability | Impact | Exposure | Mitigation | Contingency | Triggers
1 | Internet disruption (e.g. cable cut, major DNS failure) | Website becomes inaccessible globally or in specific regions | 2 | 4 | 8 | Use CDN (Content Delivery Network) and multiple DNS providers | Monitor traffic, reroute via alternate CDN nodes | Drop in traffic or server availability monitoring
2 | Data Breach (Personal information of users being exposed) | Violation of data privacy, potential legal implications, loss of trust | 2 | 5 | 10 | Use encrypted communication, implement strict access control, regular security audits | Notify users, isolate affected systems, work with cybersecurity experts | Detection of unauthorized access, abnormal server activity
3 | Outdated Medical Content | Misinformation could lead to poor decisions by users or misinterpretation by researchers | 3 | 4 | 12 | Regular content review by medical professionals | Temporary content takedown, notify users of corrections | Reports of incorrect info, periodic content audits
4 | Website inaccessible on mobile devices | Users (especially patients) unable to view research updates or resources conveniently | 4 | 2 | 8 | Implement responsive design and test across devices | Provide simplified backup content, inform users | High bounce rate from mobile, user complaints
5 | Misinterpretation of research results by non-expert readers | Patients may act on misinterpreted findings, leading to anxiety or poor health choices | 2 | 4 | 8 | Provide clear disclaimers and patient-friendly summaries | Flag and review content, add explanatory footnotes | User feedback or confusion, high misclick rate
6 | Poor maintainance of the website | Delays in updates, bug fixing, and security patching | 2 | 3 | 6 | Good documentation, resiliant back up | Temporary contractor hire or internal reassignment | Resignation, leave of absence
7 | Natural disaster (e.g. earthquake, flood) affecting data center | Website goes offline, loss of access to research and resources | 1 | 5 | 5 | Host on cloud services with geographically distributed data centers (e.g., AWS/Azure) | Failover to backup hosting, notify users via social media or email | Disaster alerts in data center region
8 |  |  | 0 | 0 | 0
9 |  |  | 0 | 0 | 0
10 |  |  | 0 | 0 | 0
11 |  |  | 0 | 0 | 0
12 |  |  | 0 | 0 | 0
13 |  |  | 0 | 0 | 0
14 |  |  | 0 | 0 | 0
15 |  |  | 0 | 0 | 0
16 |  |  | 0 | 0 | 0
17 |  |  | 0 | 0 | 0
18 |  |  | 0 | 0 | 0
19 |  |  | 0 | 0 | 0
20 |  |  | 0 | 0 | 0
Note on D8: Articulate the scale being used for probability inside of the parenthesis. E.g. (1-100%) Note: 100% would mean the item is no longer a risk and has become a problem.
Note on E8: Articulate the scale being used for impact inside the parenthesis. E.g. (1-10). Note: scale must have the same range as the probability.
Note on A9: Use this column as the risk identifier which, allows each risk to be uniquely identified.
Note on B9: Use this column to capture the "likely cause" of the risk. Be detailed enough so that you can start forming mitigation plans.
Note on C9: Use this column to capture the result of the risk, should it happen. If the consequences cannot be mitigated, you will have to dealt with them in a contingency plan.
Note on D9: Use this column to estimate the probability the risk will occur. Suggest using a percentage-based scale (1-99%).
Note on E9: Use this column to estimate the amount of impact or severity of the risk.
Note on F9: This column is computed as probability x impact. Once all risks have been entered, sort by this column to identify your biggest risks.
Note on G9: Use this column to document what plans the team has to prevent the risk or to reduce the impact before occurance. This may require creating a separate, more detailed plan.
Note on H9: Use this column to identify what will need to be done if the risk becomes reality. This may require creating a separate, more detailed plan.
Note on I9: Use this column to identify what would prompt you to execute the contingency plan. A trigger is usually a date or some sort of threshold.

## Possible Risks
Possible Risks - (Use For Risk Identification)
Organization:
Initiative, Project, and/or Engagement:
Date:
Possible Risks | Designations | Action / Disposition of Concerns, Issues, and Problems
List possible risks identified from brainstorming, interviews, and/or risk knowledge bases | Designate a concern, issue, and problem with an X and Designate a risk with and R | Define the appropriate action for each item designated X in the previous column. Potential actions include "consolidate", "escalate", "refer", "restate", "treat as out of scope", or treat as a risk and change designation in previous column to an R

## Risk Identification
Risk Identification - (Use For Risk Analysis and Prioritization)
Organization:
Iniative, Project, and/or Engagement:
Date:
Possible Risks | Identification Number | Classification / Category | Conditions | Consequences
Place the "R" designated items from the Possible Risks worksheet here | Use a number to uniquely identify each risk | • People - Customer - End User - Sponsors - Stakeholders - Personnel - Organization - Skills - Politics - Morale • Process - Mission and Goals - Decision Making - Project Characteristics - Budget, Costs, and Schedules - Requirements - Designs - Building - Testing • Technology - Security - Development and Test Environment - Tools - Deployment - Support - Operational Environment - Availability • Environmental - Legal - Regulatory - Competition - Economic - Technology - Business | Identify the cause of the risk | Define the potential result of the risk - there may be multiple consequences for each condition and some consequences can also be conditions

## Risk Analysis & Prioritization
Risk Analysis and Prioritization - (Use For Risk Planning)
Organization:
Iniative, Project, and/or Engagement:
Date:
ID Number | Priority / Order | Probability (Numeric) | Impact (Numeric) | Exposure (Numeric) | Exposure Recipient (Text)
|  | Likelihood of the Risk Condition occurring, with 1% - 30% for low, 31% - 70% for medium, and 71% - 100% for high | Effect of the Risk Consequence, with 1 - 3 for low; 4 - 7 for medium, 8 - 10 for high, and 100 for catastrophic ratings | Calculated by multiplying Risk Probability times Risk Impact, and used as the basis for ordering and prioritizing Risks | Identify who will be affected by the risk exposure (e.g., Client, Partner, & Microsoft)

## Risk Planning
Risk Planning - (Use For Risk Costing)
Organization:
Initiative, Project, and/or Engagement:
Date:
ID Number | Priority / Order | Mitigation Plans | Contingency Plans | Triggers | Responsible Person | Deliverables | Activities And Tasks | Dependencies | Time Frames | Due Dates | Resource Requirements
|  | Identify what must be done to reduce the probability of the risk condition occurring | Identify what must be done to reduce the impact of the risk consequence | Identify the criteria for determining when to initiate risk contingency plans | Identify the person responsible for each risk plan | Identify the deliverables that will be created by each risk plan | Identify the tasks and associated activities that will create the deliverables for each risk plan | Identify the tasks/activities that are dependent upon each other within each risk plan | Identify the start and complete dates for each risk plan | Identify the due date for each deliverable of the risk plan | Identify the skills, person hours, equipment, facilities, hardware, software and other resources needed for each deliverable of the risk plan (enter as individual and separate line items)

## Risk Costing
Risk Costing
Organization:
Initiative, Project, and/or Engagement:
Date:
ID Number | Priority / Order | Resource Requirements | Resource Unit Cost | Resource Total Cost | Risk Plan Total Cost | Margin | Preferred Price | Competition Anticipated Price | Customer Anticipate Price | Proposed Price
|  | Identify the skills, person hours, equipment, facilities, hardware, software and other resources needed for each deliverable of the risk plan (enter as individual and separate line items) | The actual or estimated unit cost for each of the individual resource requirement line items | Calculate the total cost for each resource requirement line item. Multiply each individual resource requirement by its associated unit cost | Calculate the estimated total cost for implementing each risk plan. Add all resource total costs for each resource unit cost line item | Identify the desired return on investment for each risk plan, expressed as a percentage | Calculate the favored price to the customer in taking responsibility for and implementing each risk plan. Multiplying the margin percentage by the total cost for each risk plan and add the results to the total cost of each risk plan | Identify what competitors would charge the customer if they took responsibility for and implemented each risk plan | Estimate what the customer would consider an acceptable price for implementing each risk plan | Identify the price to be submitted to the customer to take responsibility for and implement each risk plan. Balance among the preferred price, competitive anticipated price, and customer anticipated price

## Disclaimer
Ó 2002 Microsoft Corporation. All rights reserved.
The information contained in this document represents the current view of Microsoft Corporation on the issues discussed as of the date of publication. Because Microsoft must respond to changing market conditions, it should not be interpreted to be a commitment on the part of Microsoft, and Microsoft cannot guarantee the accuracy of any information presented after the date of publication.
This document is for informational purposes only. MICROSOFT MAKES NO WARRANTIES, EXPRESS OR IMPLIED, IN THIS DOCUMENT.